Table – SDDC Stage 1 Early Enabling Works Submission Tracker (13/09/2019)

| Requirement | Submitted / Approved? | Documents submitted (inc reference) | Comments |
| --- | --- | --- | --- |
| Requirement 3 – Stages of authorised development | Submitted: 13/09/19 | Discharge of Requirements Submission 1 letter (Doc Ref: WCGP DRS1.1) Requirement 3 – Stages of Authorised Development (Doc Ref: WCGP DOR3) Willington Pipeline AGI General Arrangement Layout rev 02 (Drawing No: UKP/WLC/AP1) Willington AGI Early Enabling Works (Doc Ref: WCGP DRS1.2) |  |
| Requirement 4 – Detailed Design Approval | Submitted: 13/09/19 | Discharge of Requirements Submission 1 letter (Doc Ref: WCGP DRS1.1) |  |
| Requirement 5 – Landscaping | Submitted: 13/09/19 | Discharge of Requirements Submission 1 letter (Doc Ref: WCGP DRS1.1) |  |
| Requirement 6 – Hedgerows and Trees | Submitted: 13/09/19 | Discharge of Requirements Submission 1 letter (Doc Ref: WCGP DRS1.1) |  |
| Requirement 8 – Public Rights of Way | Submitted: 13/09/19 | Discharge of Requirements Submission 1 letter (Doc Ref: WCGP DRS1.1) |  |
| Requirement 12 – Soil handling and restoration | Submitted: 13/09/19 | Discharge of Requirements Submission 1 letter (Doc Ref: WCGP DRS1.1) Willington Pipeline AGI General Arrangement Layout rev 02 (Drawing No: UKP/WLC/AP1) |  |
| Requirement 13 – Agricultural land drainage | Submitted: 13/09/19 | Discharge of Requirements Submission 1 letter (Doc Ref: WCGP DRS1.1) Willington Pipeline AGI General Arrangement Layout rev 02 (Drawing No: UKP/WLC/AP1) |  |
| Requirement 7 - Construction traffic and highway accesses | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES | Consultation with Derbyshire CC Highways required before submission. |
| Requirement 9 – Temporary fencing and other means of enclosure | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES |  |
| Requirement 10 – Surface Water Drainage and Water Discharge | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES |  |
| Requirement 11 – Contaminated land and ground water | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES |  |
| Requirement 14 – Archaeology | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES | Consultation with Derbyshire CC Archaeologists and Historic England required before submission. |
| Requirement 15 – Ecological Management Plan | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES |  |
| Requirement 16 – Temporary external lighting | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES |  |
| Requirement 17 – Control of noise during construction and maintenance | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES |  |
| Requirement 19 – Control of dust emissions | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES |  |
| Requirement 20 – European Protected Species | Submission being prepared | TO BE POPULATED WITH DOCUMENT TITLES / REFERENCES |  |